## Predicted
Data Analytics Project |  | Key:
Completed by: Nicholas Falla |  | # task | \@ milestone |  | ## PSM activity
Note: each interval represents a day in the week (Mon-Fri) | [10 empty] | School Holiday break
| Week starting 18/3 |  |  |  |  | Week starting 25/3 |  |  |  |  | Week starting 1/4 |  |  |  |  | Week starting 8/4 |  |  |  |  | Week starting 15/4 |  |  |  |  | Week starting 22/4 |  |  |  |  | Week starting 29/4 |  |  |  |  | Week starting 6/5 |  |  |  |  | Week starting 13/5 |  |  |  |  | Week starting 20/5 |  |  |  |  | Week starting 27/5 |  |  |  |  | Week starting 3/6 |  |  |  |  | Week starting 10/6 |  |  |  |  | Week starting 17/6 |  |  |  |  | Week starting 24/6 |  |  |  |  | Week starting 1/7 |  |  |  |  | Week starting 8/7 |  |  |  |  | Week starting 15/7 |  |  |  |  | Week starting 22/7 |  |  |  |  | Week starting 29/7 |  |  |  |  | Week starting 5/8 |  |  |  |  | Week starting 12/8
Tasks: | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5
Preliminary:
Research question
# brainstorm ideas
# finalise research question
# locate data sources
# analyse data sources
\@ complete research question
\@ submit research question
Gantt chart
# identify tasks
# allocate durations
# identify milestones
# identify dependencies
# format Gantt chart
\@ complete Gantt chart
\@ submit Gantt chart
Analysis:
Analysis report
# document list of data requirements
## document requirements
## document constraints
## formulate scope
# analyse requirements
# prepare report
\@ complete analysis report
\@ submit analysis report
Data acquisition
# prepare primary research techniques
# conduct primary reseach
# document primary research
# collect secondary research
# organise / categorise data
# reference data
\@ complete data acquisition
\@ submit data acquisition
Design:
Design folio
# prepare evaluation
# develop three design ideas
# evaluate design ideas
# further develop chosen idea
# analyse design ideas
\@ complete design folio
\@ submit design folio
Development:
Database/spreadsheet
# develop database or spreadsheet
# manipulate data
# validate input data
# test output information
\@ complete database/spreadsheet
\@ submit database/spreadsheet
Infographic or dynamic data visualisation
# develop infographic or dynamic data visualisation
# validate input data
# test output information
\@ complete infographic or dynamic data visualisation
\@ submit infographic or dynamic data visualisation
File management
# prepare file management plan
# prepare security plan
# document file management and security report
\@ complete file management
\@ submit file management
Evaluation:
Evaluation strategy and report
# prepare evaluation strategies
# complete solution evaluation
# document evaluation findings
\@ complete evaluation strategy and report
\@ submit evaluation strategy and report
Assessment of the project plan
# adjust original Gantt chart
# provide annotations for each change
# document effectiveness of Gantt chart
\@ complete assessment of the project plan
\@ submit assessment of the project plan