## Predicted
Data Analytics Project |  | Key:
Completed by: Nicholas Falla |  | # task | \@ milestone |  | ## PSM activity
Note: each interval represents a day in the week (Mon-Fri) | [10 empty] | School Holiday break
| Week starting 18/3 |  |  |  |  | Week starting 25/3 |  |  |  |  | Week starting 1/4 |  |  |  |  | Week starting 8/4 |  |  |  |  | Week starting 15/4 |  |  |  |  | Week starting 22/4 |  |  |  |  | Week starting 29/4 |  |  |  |  | Week starting 6/5 |  |  |  |  | Week starting 13/5 |  |  |  |  | Week starting 20/5 |  |  |  |  | Week starting 27/5 |  |  |  |  | Week starting 3/6 |  |  |  |  | Week starting 10/6 |  |  |  |  | Week starting 17/6 |  |  |  |  | Week starting 24/6 |  |  |  |  | Week starting 1/7 |  |  |  |  | Week starting 8/7 |  |  |  |  | Week starting 15/7 |  |  |  |  | Week starting 22/7 |  |  |  |  | Week starting 29/7 |  |  |  |  | Week starting 5/8 |  |  |  |  | Week starting 12/8
Tasks: | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5
Preliminary:
Research question
# brainstorm ideas
# finalise research question
# locate data sources
# analyse data sources
\@ complete research question
\@ submit research question
Gantt chart
# identify tasks
# allocate durations
# identify milestones
# identify dependencies
# format Gantt chart
\@ complete Gantt chart
\@ submit Gantt chart
Analysis:
Analysis report
# document list of data requirements
## document requirements
## document constraints
## formulate scope
# analyse requirements
# prepare report
\@ complete analysis report
\@ submit analysis report
Data acquisition
# prepare primary research techniques
# conduct primary reseach
# document primary research
# collect secondary research
# organise / categorise data
# reference data
\@ complete data acquisition
\@ submit data acquisition
Design:
Design folio
# prepare evaluation
# develop three design ideas
# evaluate design ideas
# further develop chosen idea
# analyse design ideas
\@ complete design folio
\@ submit design folio
Development:
Database/spreadsheet
# develop database or spreadsheet
# manipulate data
# validate input data
# test output information
\@ complete database/spreadsheet
\@ submit database/spreadsheet
Infographic or dynamic data visualisation
# develop infographic or dynamic data visualisation
# validate input data
# test output information
\@ complete infographic or dynamic data visualisation
\@ submit infographic or dynamic data visualisation
File management
# prepare file management plan
# prepare security plan
# document file management and security report
\@ complete file management
\@ submit file management
Evaluation:
Evaluation strategy and report
# prepare evaluation strategies
# complete solution evaluation
# document evaluation findings
\@ complete evaluation strategy and report
\@ submit evaluation strategy and report
Assessment of the project plan
# adjust original Gantt chart
# provide annotations for each change
# document effectiveness of Gantt chart
\@ complete assessment of the project plan
\@ submit assessment of the project plan

## Actual
Data Analytics Project |  | Key:
Completed by: Nicholas Falla |  | # task | \@ milestone |  | ## PSM activity
Note: each interval represents a day in the week (Mon-Fri) | [10 empty] | School Holiday break
| Week starting 18/3 |  |  |  |  | Week starting 25/3 |  |  |  |  | Week starting 1/4 |  |  |  |  | Week starting 8/4 |  |  |  |  | Week starting 15/4 |  |  |  |  | Week starting 22/4 |  |  |  |  | Week starting 29/4 |  |  |  |  | Week starting 6/5 |  |  |  |  | Week starting 13/5 |  |  |  |  | Week starting 20/5 |  |  |  |  | Week starting 27/5 |  |  |  |  | Week starting 3/6 |  |  |  |  | Week starting 10/6 |  |  |  |  | Week starting 17/6 |  |  |  |  | Week starting 24/6 |  |  |  |  | Week starting 1/7 |  |  |  |  | Week starting 8/7 |  |  |  |  | Week starting 15/7 |  |  |  |  | Week starting 22/7 |  |  |  |  | Week starting 29/7 |  |  |  |  | Week starting 5/8 |  |  |  |  | Week starting 12/8
Tasks: | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5
Preliminary:
Research question
# brainstorm ideas
# finalise research question
# locate data sources
# analyse data sources
\@ complete research question
\@ submit research question
Gantt chart
# identify tasks
# allocate durations
# identify milestones
# identify dependencies
# format Gantt chart
\@ complete Gantt chart
\@ submit Gantt chart
Analysis:
Analysis report
# document list of data requirements
## document requirements
## document constraints
## formulate scope
# analyse requirements
# prepare report
\@ complete analysis report
\@ submit analysis report
Data acquisition
# prepare primary research techniques
# conduct primary reseach
# document primary research
# collect secondary research
# organise / categorise data
# reference data
\@ complete data acquisition
\@ submit data acquisition
Design:
Design folio
# prepare evaluation
# develop three design ideas
# evaluate design ideas
# further develop chosen idea
# analyse design ideas
\@ complete design folio
\@ submit design folio
Development:
Database/spreadsheet
# develop database or spreadsheet
# manipulate data
# validate input data
# test output information
\@ complete database/spreadsheet
\@ submit database/spreadsheet
Infographic or dynamic data visualisation
# develop infographic or dynamic data visualisation
# validate input data
# test output information
\@ complete infographic or dynamic data visualisation
\@ submit infographic or dynamic data visualisation
File management
# prepare file management plan
# prepare security plan
# document file management and security report
\@ complete file management
\@ submit file management
Evaluation:
Evaluation strategy and report
# prepare evaluation strategies
# complete solution evaluation
# document evaluation findings
\@ complete evaluation strategy and report
\@ submit evaluation strategy and report
Assessment of the project plan
# adjust original Gantt chart
# provide annotations for each change
# document effectiveness of Gantt chart
\@ complete assessment of the project plan
\@ submit assessment of the project plan

## LogAndEvaluation
Preliminary: | Both the research question and gantt chart tasks were completed to schedule.
Analysis: | Analysis report was completed to schedule.
Data acquisition took 20 days longer than originally scheduled in order to get as many responses as possible for more accurate data, so the online survey was left open to gain more responses while other tasks were completed.
Design: | The design folio tasks were completed to schedule.
Development: | The database tasks and infographic tasks were completed and submitted 2 week later than planned due to the data acquisition being delayed.
The file management tasks were completed on time originally however it was required to be re-submitted 10 weeks later with evidence of implementation.
Evaluation: | The evaluation report and project plan assessment tasks were comleted within the allocated time predicted, however the due date of the infographic was delayed a week, so the start point of these tasks was a week later, and finished a week later.
The project plan provided a clear list of the tasks that needed to be completed, their approximate duration and the order in which they needed to occur.
Once the project was underway, the project plan could be checked at regular intervals to see how tasks were tracking against the original plan. This included
knowing how many tasks were currently being worked on, whether the task durations were taking the time period specified, and if they were being
completed in the correct order. The plan could also be adjusted during the completion of the project, to give an update on realistic timelines if tasks already
completed were either ahead of schedule or behind schedule
The project plan provided an obvious black diamond indicator to represent when each of the ten major tasks needed to be completed and submitted. With
many competing pressures from other subjects and personal commitments, the project plan could be checked at regular intervals to ensure that tasks were
running as expected. If any tasks were taking longer than anticipated to complete, it was clear that things would need to speed up slightly in order to ensure
the remaining tasks are completed on time (or by the delayed due date).